FIMS Flexible Compliance Implementation Roadmap

Adaptive Milestone Framework & Variable Velocity Pacing (8 – 14 Weeks)

1. Executive Summary & Flexible Strategy

This flexible implementation roadmap establishes an adaptive, phased delivery schedule for FIMS compliance features. Rather than forcing a single rigid timeline, it accommodates different resource capacities (1 vs. 2 engineers) and allows organizations to prioritize compliance tracks based on target market requirements (e.g., Fast-Tracking PCI DSS for retail, or postponing SWIFT CSP until banking customer onboarding).

Flexible Compliance Deployment Tracks

| Track Tier | Target Environment | Flexible Window | Key Deliverables Included |
| --- | --- | --- | --- |
| Track A: Core Hardening | Internal Staging & Lab Testing | Weeks 1 – 3 | JWT/RBAC Auth, AES-256 DPAPI Encryption, HMAC Signed Logs, TLS |
| Track B: Commercial Suite | Enterprise SaaS & PCI DSS Retail | Weeks 4 – 8 | Kernel Real-time Watcher, User SID Attribution, SIEM Exporter, Compliance UI |
| Track C: Financial Suite | Tier-1 Banks & SWIFT Gateways | Weeks 9 – 12 | SWIFT SAG Discovery, Live DB Schema Hooks, Watchdog Heartbeat, Signed PDFs |

Resource Pacing & Velocity Options

| Engineering Capacity | Weekly Commitment | Full Suite Duration | Risk & Flexibility Profile |
| --- | --- | --- | --- |
| Accelerated (2 FTE) | 80 Hours / Week | 8 Weeks (Fast) | Minimal buffer; rapid delivery for imminent audits. |
| Standard (1 FTE) | 40 Hours / Week | 12 Weeks (Balanced) | Recommended; includes 2 buffer weeks for QA & Penetration Testing. |
| Part-Time / Modular (0.5 FTE) | 20 Hours / Week | 16 Weeks (Extended) | Low-impact execution; feature releases spread over 4 months. |

2. Flexible Milestone Breakdown

Milestone 1: Security Hardening Core (Weeks 1 – 3 Window)

• Work Package 1.1: JWT Authentication & Role-Based Access Control (RBAC) in server.py
• Work Package 1.2: AES-256 Baseline Store Encryption via Windows DPAPI in baseline_store.py
• Work Package 1.3: HMAC-SHA256 Signed Append-Only Audit Logging in logger.py
• Work Package 1.4: TLS Security & Header Hardening

Milestone 2: Real-time Kernel Engine & SIEM Alerts (Weeks 4 – 7 Window)

• Work Package 2.1: Real-time Kernel Event Monitoring (ReadDirectoryChangesW) in monitor.py
• Work Package 2.2: User Identity & SID Attribution Engine via Windows Audit Event Logs
• Work Package 2.3: SIEM Alert Exporter (Syslog UDP/TCP/TLS, CEF, Webhooks, Email)
• Work Package 2.4: Anti-Tampering Process Watchdog Daemon

Milestone 3: Compliance Dashboard UI & Audit Reports (Weeks 8 – 10 Window)

• Work Package 3.1: NIST SP 800-53 & ISO 27001 Control-Tagged PDF Audit Reports in report.py
• Work Package 3.2: Interactive React Compliance Dashboard UI Component (ComplianceDashboard.jsx)
• Work Package 3.3: Dual-Control Change Approval Workflow & Digital X.509 Signatures

Milestone 4: SWIFT CSP Banking Compliance Pack (Weeks 11 – 13 Window)

• Work Package 4.1: SWIFT Alliance Gateway (SAG/SAA) Auto-Discovery Wizard in OnboardingWizard.jsx
• Work Package 4.2: High-Security Encrypted Key Storage for SWIFT Routing Tables & Binaries
• Work Package 4.3: Live Database Schema (DDL) Snapshots for Financial Lineage & DB Tables
• Work Package 4.4: Banking Network Self-Integrity Heartbeat & Redundant Daemon Pairing

Milestone 5: Audit Buffer & Final Verification (Weeks 13 – 14 Window)

• Work Package 5.1: Third-Party QSA / SWIFT Assessor Penetration Testing & Audit Sign-Off
• Work Package 5.2: Production Readiness & Release Packaging

3. Strategic Flexibility & Phase Swapping Guidelines

1. Modular Phase Swapping: If a banking client requests SWIFT CSP early, Milestone 4 can be swapped with Milestone 3 right after Milestone 1.
2. Minimum Viable Compliance (MVC): Releasing Milestone 1 + Milestone 2 allows immediate PCI DSS 4.0 and ISO 27001 commercial deployment in 6-8 weeks.
3. Buffer Management: Each phase includes 3-5 days of built-in contingency buffer for regression testing and auditor feedback.